## Cover Sheet
Project Controls Workbook
Project Number | 90xxxx
Project Name | <Project name>
Project Manager | <PM name>
Project Owner | <Project Owner name>

## Risks
|  |  | RISK REGISTER - Risks (threats) for <Project name> Project | [5 empty] | RISK REGISTER - Risks (threats) for <Project name> Project
|  | IDENTIFY |  |  |  |  | ASSESS |  |  |  |  | PLAN |  | MONITOR & ACT
Risk ID | Category | Title | Description | Impact | Status | Likelihood | Consequence | Risk Rating | Date Raised | Source | Owner | Response | Response Plan | Action taken / comments | Date Closed
R01 | Business change | (Example) Students have privacy concerns | Students may be concerned of a "big brother" approach in the resulting system. Collection of personal data may seem irrelevant to them in this context. | Concerned students refuse to use the service, leading to slow or partial uptake, therefore limited usability of the resulting data. | Assigned | Moderate | Moderate | Moderate 3 | 2018-11-20 | Student Union email to DVC SLT. | Patrick Player (AD, Student Systems, Student Admin) | Mitigate | Identify thje minimum data set required for good running of the service and privacy requirements to frame a workable policy. Also leaverage experience from other local universities that have deployed a similar system. Engage ACU Legal early in the project to ensure the project's viability and provide guidance on how to proceed including the change & comms strategy. Involve MER as required or directed. | 20/11/18 FR: Risk raised after receiving the email from DVS SLT to the project. 5/12/18 TG: Risk assessed, response plan created. Being monitored.
R02 | [7 empty] | #N/A
R03 | [7 empty] | #N/A
R04 | [7 empty] | #N/A
R05 | [7 empty] | #N/A
R06 | [7 empty] | #N/A
R07 | [7 empty] | #N/A
R08 | [7 empty] | #N/A
R09 | [7 empty] | #N/A
R10 | [7 empty] | #N/A
R11 | [7 empty] | #N/A
R12 | [7 empty] | #N/A
R13 | [7 empty] | #N/A
R14 | [7 empty] | #N/A
R15 | [7 empty] | #N/A
R16 | [7 empty] | #N/A
R17 | [7 empty] | #N/A
R18 | [7 empty] | #N/A
R19 | [7 empty] | #N/A
R20 | [7 empty] | #N/A
R21 | [7 empty] | #N/A
R22 | [7 empty] | #N/A
R23 | [7 empty] | #N/A
R24 | [7 empty] | #N/A
R25 | [7 empty] | #N/A
R26 | [7 empty] | #N/A
R27 | [7 empty] | #N/A
R28 | [7 empty] | #N/A
R29 | [7 empty] | #N/A
R30 | [7 empty] | #N/A
R31 | [7 empty] | #N/A
R32 | [7 empty] | #N/A
R33 | [7 empty] | #N/A
R34 | [7 empty] | #N/A
R35 | [7 empty] | #N/A
R36 | [7 empty] | #N/A
R37 | [7 empty] | #N/A
R38 | [7 empty] | #N/A
R39 | [7 empty] | #N/A
R40 | [7 empty] | #N/A
Note on A3: Risk ID is a unique running number for the risk. A prefix can be added to e.g. identify the project in a program (e.g. "CB-R08").
Note on B3: Which aspect of the project will be impacted if the uncertainty materialises?
Note on C3: The name of the risk in one short sentence. Any reasons and explanations are given in the Description field. E.g. "Equipment installations delayed" or "Consultancy costs significantly lower than expected".
Note on D3: A brief bescription of the opportunity or threat giving the key reason or background for it.
Note on E3: What will happen to the project if the risk materialises but is not responded to? A short pragraph with one or two key impacts.
Note on F3: Status of the risk as of now.
Note on G3: How likely is it that the opportunity or threat will happen?
Note on H3: How big will the consequences be if the opportunity or threat materialises?
Note on I3: Resulting rating = likelihood * consequence. Use this to prioritise your attention and project team's efforts to help or protect the project.
Note on J3: When was this entry added, i.e. the risk identified and added to the register?
Note on K3: Where or by whom was the risk identified? This can be any individual, a meeting / workshop, specific event in the project environment, message or document, etc.
Note on L3: Who owns this risk? This person is typically in a senior position and can prioritise and direct staff time and ACU resources to work on the opportunity or threat when needed.
Note on M3: How is the project going to act with this opportunity or threat?
Note on N3: A brief description of the action to be taken.
Note on O3: A log / diary of the action taken to benefit from the opportunity or protect against a threat. All entries should be dated and have name or initials (e.g. "15/10/18 WG"). Addition of a new entry, assessments, assignments, etc need also to be logged.
Note on P3: When was this risk entry closed, i.e. the monitoring of it or work on it was completed or stopped?

## Issues
ISSUE REGISTER for <Project name> Project
|  |  |  | IDENTIFY & PLAN |  |  |  |  | ACTION
Issue ID | Status | Category | Title | Description | Impact Summary | Priority | Mitigation | Action taken / Comments | Reported by | Owner | Date Raised | Target Date / Actual finish
I01 | New | Technical | (Example) Multi-Vendor Wi-Fi Infrastructure | This environment will not support the "location aware" requirements as the installed mixed acccess points are incompatible with the "location aware" data collection application. |  | Medium | Create a single vendor access point environment | 14/11/18 MG: Xirius access point replacement strategy has been identified. |  |  | 2018-11-05 | 2018-12-10
I02
I03
I04
I05
I06
I07
I08
I09
I10
I11
I12
I13
I14
I15
I16
I17
I18
I19
I20
I21
I22
I23
I24
I25
I26
I27
I28
I29
I30
I31
I32
I33
I34
I35
I36
I37
I38
I39
I40
Note on A3: Issue ID is a unique running number for the issue. A prefix can be added to e.g. identify the project in a program (e.g. "CB-I08").
Note on B3: Status of the issue as of now.
Note on C3: Which aspect of the project has been impacted of the unplanned event?
Note on D3: The name of the issue in one short sentence. Any reasons and explanations are given in the Description field. E.g. "Equipment installations delayed" or "Consultancy costs significantly lower than expected".
Note on E3: A brief bescription of the issue, giving the key reason or background for it.
Note on F3: A brief summary of the impact to the project (e.g. added work required, changes to time or budget).
Note on G3: The urgency of the issue resolution. * Low - Project stays within tolerance. Issue is worked on when possible. * Medium - Project likely to exceed the tolerance. Work is scheduled and managed. * High - Showstopper. Work commences immediately and continues until resolution.
Note on H3: A brief description of the action to be taken.
Note on I3: A log / diary of the action taken to action and resolve the issue. All entries should be dated and have name or initials (e.g. "15/10/18 WG"). Addition of a new entry, assessments, assignments, etc need also to be logged.
Note on J3: Where or by whom was the issue identified? This can be any individual, a meeting / workshop, specific event in the project environment, message or document, etc.
Note on K3: Who owns this issue? This person leads the work to resolve the issue (typically a Technical Lead, team supervisor or manager, or similar).
Note on L3: When was this entry added, i.e. the issue identified and added to the register?
Note on M3: When do we plan or this issue must to be resolved by? For issues alread resolved this date is the actual closure date.

## Changes
PROJECT CHANGE REGISTER for <Project name> Project
|  | IDENTIFY | [6 empty] | ACTION
Change ID | Category | Title | Description | Priority | Phase | Status | Date raised | Owner | Target date | Action taken / comments
C01 | Quality | (Example) Change equipment configuration task to a vendor service to exploit an opportunity to increase quality. | Vendor service to pre-configure equipment guarantees uniform quality and reduces the effort to configure & test in-house. This is expected to increase the quality of the outputs and free up 8 days of staff / contractor time to BAU work. Cost impact expected is +$4,000 Capex, -$8,000 Opex, and +$2,000 overhead annually. | Medium | Implement | Submitted | 2018-11-14 | Wil Daniels (AD Infrastructure, IT) | 2018-12-14 | 14/11/18 WD: Opportunity R01 identified as benefiting of a project change, a Request for Change (RFC) drafted. 19/11/18 WD: RFC submitted to Project Board for approval in the 28/11 meeting.
C02
C03
C04
C05
C06
C07
C08
C09
C10
C11
C12
C13
C14
C15
C16
C17
C18
C19
C20
C21
C22
C23
C24
C25
C26
C27
C28
C29
C30
C31
C32
C33
C34
C35
C36
C37
C38
C39
C40
Note on A3: Change ID is a unique running number for the project change. It needs to match any ID's used in the Project Change Request form when presenting the change for approval. A prefix can be added to e.g. identify the project in a program (e.g. "CB-C08").
Note on B3: Which aspect of the project is impacted by this change?
Note on C3: The name of the change in one short sentence. Any reasons and explanations are given in the Description field. E.g. "Two months additional time required for equipment installations" or "Budget adjustment requested due to lower consultancy costs".
Note on D3: A brief bescription of the change, giving the key reason or background for it and impact to the project.
Note on E3: The urgency of the change. * Low - The change is useful but can wait, if required. * Medium - The change is presented in the next scheduled Project Board (or similar) meeting. Work needs to be scheduled and managed within the current phase. * High - Showstopper. This change requires immediate attention and the project is unable to continue successfully until it is resolved.
Note on F3: The project lifecycle phase the change applies to.
Note on G3: Status of the project change as of now.
Note on H3: When was this entry added, i.e. the project change identified and added to the register?
Note on I3: Who owns this project change? This person leads the work to complete the change, if approved (typically the Project Manager for cost / time / scope, and specialist or manager for deliverables or resourcing).
Note on J3: When do we plan or this project change must to be implemented by?
Note on K3: A log / diary of the action taken to identify, present and implement a project change. All entries should be dated and have name or initials (e.g. "15/10/18 WG"). Addition of a new entry, assessments, assignments, etc need also to be logged.

## Lessons
LESSONS LEARNED from <Project name> Project
Lesson # | Category | Situation / cause | Analysis / Discussion | Lesson Learned / Recommendation | Assign to | Added date | Received from
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
Note on D3: What action was taken? What was the result? What was the root cause of the problem? What may have yielded a better result? How can a similar situation be identified in the future?
Note on F3: Individual who is responsible for implementing the recommendation if there are specific actions to following on from the lesson.

## Status colours and changes
GUIDANCE FOR STATUS COLOURS AND PROJECT CHANGES
For business and IT projects
Below is guidance for setting project status colours ("traffic lights") in status reporting and when to submit a project change request to approve new forecasts.
Every project encounters change over time. It may be due to the actual work being done faster or slower than estimated or unexpected delays or costs. In some cases, the project environment, requirements and scope changes, leading to re-forecasting of the work and costs ahead.
A red light will trigger a Project Change Request (PCR) regardless which aspect is on red. The PCR is submitted to the relevant project governance group.
If the project timeline (schedule), budget (cost) or benefits change, the Project Business Case is updated and re-approved by the Executive Sponsor. If other aspects change, the Project Initation Document (PID) and associated plans and schedule are updated and re-approved by the Project Owner.
After a change has been approved, the project is re-baselined. From there on, the reporting is based on that new baseline.
OVERALL STATUS OF A PROJECT
|  |  | GREEN | AMBER | RED
|  | Projects in the PPM System: | All green or 1 amber | 2 or more amber and 0 red | 1 or more red
|  | Aspects reported on all projects: | All green or 1-2 amber | 3 or more amber and 0 red | 1 or more red
|  | If also additional aspects are reported, please use the following: | All green or 1-3 amber | 4 or more amber and 0 red | 1 or more red
INDIVIDUAL ASPECTS OF A PROJECT
| RED | AMBER | GREEN | AMBER | RED | Reference point | Will impact the…
Reported on all projects (where possible)
Schedule | More than 2 monts early | 2 weeks - 2 months early | +/- 2 weeks from approved finish date | 2 weeks - 2 months late | More than 2 months late | Project completion milestone vs the timeline approved in Project Business Case. | Project Business Case
Cost (EAC) | Equal or less than 80% | 81 - 90% | 91 - 100% | 101 - 110% | More than 110% - or - Actuals > budget (regardless of the spend) | Estimate at completion (EAC) vs the approved budget in Project Business Case. - or - Actuals in T1 vs the approved budget.
Benefits | Equal or less than 70% | 71 - 90% | 91 - 110% | 111 - 130% | More than 130% | Value of output benefits as defined in the Project Business Case.
Risks |  |  | Max 2 moderate risks, 0 high risks | 3 or more moderate risks or 1 high risk | 2 or more high risks | Count of open risks in the project risk register. | PID
Issues |  |  | Max 2 medium issues, 0 high severity issues | 3 or more medium or 1 high severity issue | 2 or more high severity issues | Count of open issues in the project issue register.
Additional aspects which are monitored continuously and can be reported on
Scope |  |  | All deliverables in full (100%) | 80 - 99% can be delivered | Less than 80% can be delivered | % of deliverables / outputs completed as planned, as defined in the PID.
Quality |  |  | >95% criteria met (100% of 'must have') | 90-95% of criteria met (90-99% of 'must have') | Less than 90% of criteria met | % of quality criteria met. Criteria defined in the PID or respective quality or test plans.
Work |  |  | 0 - 110% | 110 - 120% | More than 120% | % of work forecasted vs baseline (work hours in schedule)
Resources |  |  | All resources available | 80 - 99% available | Less than 80% available | Committed availability in effort days vs the planned work in project schedule during weeks when required.

## Risk rating
RISK AND ISSUE RATINGS
Please keep this sheet intact without modifications.
For more information on risk ratings, please refer to the
ACU Risk Management Procedure
RISK
Inherent risk
Likelyhood \ Consequence | Insignificant | Minor | Moderate | Major | Catastrophic
Almost Certain | Moderate 3 | Moderate 9 | High 30 | High 90 | High 300
Likely | Moderate 1 | Moderate 3 | Moderate 10 | High 30 | High 100
Moderate | Low 0.3 | Moderate 0.9 | Moderate 3 | Moderate 9 | High 30
Unlikely | Low 0.1 | Low 0.3 | Moderate 1 | Moderate 3 | Moderate 10
Rare | Low 0.03 | Low 0.09 | Low 0.3 | Moderate 0.9 | Moderate 3
Residual risk
Original impact \ Mitigation | Effective | Satisfactory | Some Weakness | Weak
High | Moderate | Moderate | High | High
Moderate | Moderate | Moderate | Moderate | High
Low | Low | Low | Low | Moderate
Issue rating
Low - Green | Project stays within tolerance. Issue is worked on when possible.
Medium - Amber | Project likely to exceed the tolerance. Work is scheduled and managed.
High - Red | Showstopper. Issue resolution work commences immediately and continues until resolution.
RAG status explanation
Green | No problems, all tracking to plan.
Amber | Some problems exist which could impact project completion, outputs, quality, etc but are being managed within the project.
Red | Problems exist which will impact project completion, outputs, quality, etc and need specific actions / support from the Project Board.
Risk likelihoods
Almost Certain | >90%. Almost certain, is expected to occur in most circumstances.
Likely | ≥60%. Very likely, will probably occur at least once.
Moderate | ≥40%. Likely to happen at some time.
Unlikely | ≥10%. Possible but not likely.
Rare | <10%. Conceivable but unlikely. May occur in exceptional circumstances.

## Data Validation (hidden)
LOOKUPS FOR THE REGISTERS
Please do not alter!
These are set by the Portfolio Project Office to confirm with the ACU Project Management Model.
Risks |  |  |  | Risks, issues | Issues | Change Requests |  |  |  | Lessons |  | Requirements |  |  | Requirements |  |  |  | Requirements | Constraints
Category | Likelihood | Consequence | Response | Status | Category | Category | Status | Phase | Priority | Category | Benefits | Type | Status | Change & Comms | T-Shirt Sizing | Estimated Effort | Trends |  | MoSCoW | Severity
Cost | Almost Certain | Catastrophic | Accept | New | Business | Cost | New | Pre-initiate | Low | Adoption | Compliance | Project Management | Not Started | Change strategy | Small | 1 | ↑ | Weak | Must Have | Low
Quality / acceptance | Likely | Major | Escalate | Assigned | Technical | Quality | Submitted | Initiate | Medium | Delivery | Avoid cost | Presentation | In Progress | Change activity | Medium | 2 | ↔ | Some Weakness | Should Have | Medium
Scope | Moderate | Moderate | Transfer | In progress | Commercial | Scope | Approved | Plan | High | Governance | Reduce cost | Service | Test | Comms strategy | Large | 3 | ↓ | Satisfactory | Could Have | Significant
Time | Unlikely | Minor | Mitigate | Pending | Legal | Time | Completed | Implement |  | Operations | Reduce risk | Final | Delayed | Comms activity | X-Large | 5 |  | Effective | Won't Have | High
Contractual, legal | Rare | Insignificant | Avoid | Completed | Reputation | Resources | Pending / on-hold | Close |  | Requirements | Improve capacity |  | Complete |  | XX-Large | 8 |  |  |  | Extreme
Reputation |  |  |  | Rejected | Security | Other | Transferred |  |  | Other | Increase revenue |  |  |  | TBC | TBC
Business change |  |  |  |  | Constraint |  | Rejected / cancelled |  |  |  | Protect revenue
Governance |  |  |  |  | Other | [5 empty] | Improve service
Other | [10 empty] | Increase customer satisfaction
Reduce cycle time
Other
Template version | Published | Notes
v 1.0 | 2018-11-19 | First version published, contains risk + issue + change.
v 2.0 | 2019-11-11 | Updated with the refreshed PM Policy & templates. Removed opportunities from risk management (waits for ACU Risk Mgmt Model to introduce opportunities).
v3.0 | 2020-07-09 | Finetuning.
v4.0 | 2020-09-30 | Added Lessons register.